## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US 1 | Research image tampering techniques | MUST HAVE | None | Sandhiya R | 3- Completed
Sprint 1 | Sprint 1 | US 2 | Analyze dataset (CASIA) | MUST HAVE | US 1 | Sandhiya R | 3- Completed
Sprint 1 | Sprint 1 | US 3 | Finalize Resnet50 approach | MUST HAVE | US 2 | Sandhiya R | 3- Completed
Sprint 2 | Sprint 2 | US 4 | Load Dataset | MUST HAVE | US 3 | Sandhiya R | 3- Completed
Sprint 2 | Sprint 2 | US 5 | Clean & normalize dataset | MUST HAVE | US 4 | Sandhiya R | 3- Completed
Sprint 2 | Sprint 2 | US 6 | Split dataset | MUST HAVE | US 5 | Sandhiya R | 3- Completed
Sprint 3 | Sprint 3 | US 7 | Design resnet50 model | MUST HAVE | US 6 | Sandhiya R | 3- Completed
Sprint 3 | Sprint 3 | US 8 | Train model | MUST HAVE | US 7 | Sandhiya R | 3- Completed
Sprint 3 | Sprint 3 | US 9 | Evaluate model | MUST HAVE | US 8 | Sandhiya R | 3- Completed
Sprint 1 | Sprint 1 | US1 | As a developer, I want to download and organize the SROIE dataset so that I can train and test the address detection system. | MUST HAVE | None | Maheswari | 3- Completed
Sprint 1 | Sprint 1 | US 2 | As a developer, I need to load the dataset and use it for further process in the project. | MUST HAVE | US 1 | Maheswari | 3- Completed
Sprint 1 | Sprint 1 | US 3 | As a developer, I want to apply image preprocessing techniques such as resizing, grayscale conversion, and noise removal so that text detection accuracy improves. | MUST HAVE | US 2 | Maheswari | 3- Completed
Sprint 2 | Sprint 2 | US 4 | As a developer, I want to train a YOLO model using annotated SROIE images so that text regions in documents can be detected automatically. | MUST HAVE | US 3 | Bhargavi K | 3- Completed
Sprint 2 | Sprint 2 | US 5 | As a developer, I want to integrate EasyOCR to extract text from detected regions so that address information can be obtained from images. | MUST HAVE | US 4 | Bhargavi K | 3- Completed
Sprint 3 | Sprint 3 | US 6 | As a system, I want to identify and extract address-related text from OCR output so that only relevant address information is retained. | MUST HAVE | US 5 | Bhargavi K | 3- Completed
Sprint 3 | Sprint 3 | US 7 | As a user, I want the extracted address to be displayed on screen so that I can verify the information.As a user, I want the extracted address to be displayed and saved so that I can verify and reuse the detected information. | SHOULD HAVE | US 6 | Bhargavi K | 3- Completed
Sprint 1 | Sprint 1 | US 1 | Collect and organize selfie and ID image dataset | MUST HAVE | None | Deeksha H L | 3- Completed
Sprint 1 | Sprint 1 | US 2 | Preprocess images – resize, normalize, augment | MUST HAVE | US 1 | Deeksha H L | 3- Completed
Sprint 2 | Sprint 2 | US 3 | Extract face embeddings using pretrained FaceNet | MUST HAVE | US 2 | Pravalli l | 3- Completed
Sprint 2 | Sprint 2 | US 4 | Compute cosine similarity and L2 distance between pairs | MUST HAVE | US 3 | Pravalli l | 3- Completed
Sprint 2 | Sprint 2 | US 5 | Implement ensemble similarity approach (cosine + L2) | SHOULD HAVE | US 4 | Pravalli l | 3- Completed
Sprint 3 | Sprint 3 | US 6 | Perform hard negative mining on impostor pairs | SHOULD HAVE | US 5 | Pravalli l | 3- Completed
Sprint 3 | Sprint 3 | US 7 | Select optimal threshold using ROC and Youden's Index | MUST HAVE | US 6 | Devi Pragada | 3- Completed
Sprint 4 | Sprint 4 | US 8 | Evaluate model using Accuracy, F1, AUC, FAR, FRR | MUST HAVE | US 7 | Devi Pragada | 3- Completed
Sprint 4 | Sprint 4 | US 9 | Train Logistic Regression and compare with similarity method | COULD HAVE | US 8 | Devi Pragada | 3- Completed
Sprint 4 | Sprint 4 | US I0 | Save embeddings, results, and evaluation plots | MUST HAVE | US 9 | Deeksha H L | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 72 | 4 | 7 | 1 | 4 | 6 | 7 | 4 | 7 | 5 | 5 | 7 | 6 | 5 | 4
SPRINT 1 BACKLOG
US1 | T1 | Research & paper review | Day 1 | Day 2 | Sandhiya R | Design | 3- Completed | 7 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T2 | Dataset analysis & loading | Day 2 | Day 4 | Sandhiya R | Coding | 3- Completed | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T3 | Data preprocessing (clean + resize + split) | Day 5 | Day 7 | Sandhiya R | Coding | 3- Completed | 9 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T4 | Model design & training | Day 8 | Day 11 | Sandhiya R | Build | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 2 | 2 | 0 | 0 | 0
US 5 | T5 | Evaluation & tuning | Day 12 | Day 14 | Sandhiya R | System Test | 3- Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0
US1 | T1 | Download SROIE dataset from official source | Day 1 | Day 2 | Maheshwari | Coding | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T2 | Extract dataset and verify image and annotation files | Day 3 | Day 3 | Maheshwari | Coding | 3- Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T3 | Load dataset into Python environment for processing | Day 4 | Day 4 | Maheshwari | Coding | 3- Completed | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T4 | Implement image resizing for all dataset images | Day 5 | Day 5 | Maheshwari | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T5 | Apply grayscale conversion and noise removal | Day 6 | Day 6 | Maheshwari | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T6 | Configure YOLO training environment and dependencies | Day 7 | Day 7 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T7 | Train YOLO model using annotated SROIE images | Day 8 | Day 10 | Bhargavi K | Coding | 3- Completed | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0
US 5 | T8 | Install and configure EasyOCR library | Day 11 | Day 11 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
US 5 | T9 | Extract text from YOLO-detected regions using EasyOCR | Day 12 | Day 12 | Bhargavi K | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
US 6 | T10 | Implement logic to identify address text from OCR output | Day 13 | Day 13 | Bhargavi K | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
US 7 | T11 | Display extracted address on screen for verification | Day 14 | Day 14 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
US 7 | T12 | Save extracted address to output file for reuse | Day 14 | Day 14 | Bhargavi K | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Too many tampering detection techniques | reviewed multiple research papers and shortlisted methods
Sprint 1 | Day 2 | Difficulty understaning dataset differences | compared datasets and selected CASIA dataset
Sprint 1 | Day 3 | confusion in choosing model architecture | finalized resnet50 approach
Sprint 2 | Day 4 | dataset not loading properly | fixed file path and directory structure
Sprint 2 | Day 5 | dataset not loading properly | removed invalid images from dataset
Sprint 2 | Day 6 | dataset not loading properly | applied resizing to standard dimensions
Sprint 2 | Day 7 | data imbalance issue | adjusted dataset split properly
Sprint 3 | Day 8 | Difficulty designing model structure | implemented resnet50 architecture stepbystep
Sprint 3 | Day 9 | training taking too long | reduced batch size and optimized code
Sprint 3 | Day 10 | low model accuracy | tuned hyperparameters
Sprint 3 | Day 11 | overfitting problem | added dropout layers

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | Day 1 | Day 3 | Sandhiya R | Validate approach before implementation | Randomly exploringwithout direction | Documenting research finding | Finalized Resnet50 approach and dataset
2 | Sprint 2 | Day 4 | Day 7 | Sandhiya R | Check data quality before processing | Ignoring corrupted data | Breaking tasks into smaller steps | Cleaned dataset and standardized images
3 | Sprint 3 | day 8 | Day 14 | Sandhiya R | Test model on small data before full training | Running full training without validation | Monitoring accuracy and loss | Improved model performance using tuning
4 | Sprint 1 | Day 1 | Day 6 | Bhargavi K Maheshwari S | Analyze problem and select correct model approach | Randomly choosing methods without analysis | Researching different techniques | Finalized YOLOv8 and EasyOCR approach
5 | Sprint 2 | Day 7 | Day 13 | Maheswari S | Validate and clean dataset before processing | Ignoring corrupted or missing data | Organizing dataset properly | Cleaned dataset and fixed file structure
6 | Sprint 3 | Day 14 | Day 14 | Bhargavi K | Train model with validation | Running training without monitoring performance | Tracking accuracy and loss | Improved model using increasing ephocs
7